## readme1st
v1 - Seba
initial budget for the summit based on OWASP template https://docs.google.com/spreadsheets/d/1Il5fT21mhHEgZB_takzFyai-HspDQyF52dFPKW527rc/edit#gid=0
Use numbers based on assumptions to create the budget, so we can update the budget by validating or updating our assumptions

## summit 2017 budget
owasp summit 2017 |  |  |  | 12-16 June 2017
| budget | actual |  | budget | actual
summit attendees | 120 | 131 | Estimated profit | 0 | 48071.325
|  |  | refund seed fund | 150000 | 50000
|  |  | Final profit | 4607 | -1928.675
Income |  |  | Expenses
| Final |  |  | Final
seed fund owasp | 150000 | 50000 | Venue - lodges | 24549.1 | 45975.8
people covering own ticket | 120000 | 69580.5 | Catering | 32156.4 | 28559.375
Sponsorship | 0 | 17250 | Sponsored travel | 0
owasp chapters / projects | 23000 | 46400 | Professional Summit Organisation team (logistics/event-management, travel agency, workshop preparation, IT support, design, hospitality, media support) | 5000
outreach + other funded |  | 17541 | Signage | 1000
|  |  | Program | 1000
|  |  | Social activities | 2250
|  |  | t-shirts | 1800
|  |  | Website | 3000
|  |  | Badges | 600
|  |  | Office suplies | 3000
|  |  | Internet uplink | 0 | 390
|  |  | Meeting Rooms | 52387.5 | 53625
|  |  | Summit Funded | 11650 | 24150
TOTAL | 293000 | 200771.5 | TOTAL | 138393 | 152700.175
ACTUAL INCOME |  |  | ACTUAL COST
sponsors | 63650 |  | Lodges | 40690
tickets | 69580.5 |  | Venue (5 days) | 53625
invoiced | 21918 |  | Catering (full) | 3741278.125
|  |  | lodges - weekend | 5285.8

## catering
item | USD
tea/coffee (3) | 6.175
lunch | 20.8
attendees | 125
days | 5
16859.375
dinner | 13
breakfast | 6.5
drinks | 9.75
attendees | 100
days | 4
11700
Total 5 days | 28559.375

## Assumptions
all budget is in USD + 20% VAT | BUDGET | Status 6-Mar
# volunteers | 5
summit ticket - 24h | 1800
summit ticket - 8h | 600
owasp seed | 150000
# attendees (full) | 40
# attendees 8h | 80
# of sponsored attendees | 0
number of summit days | 5
average travel per attendee | 600
sponsor income | 0
project/chapter donactions | 23000 | 22500 | additional 500 (NYC)
social event cost per attendee | 50
cost of t-shirt | 15
website cost (layout/hosting) | 3000
badge cost | 5
Org team cost | 5000 |  | includes travel/accomodation. This might decrease with help from OWASP staff
Conversion rate from GBP | 1.24
Office supplies | 3000
Internet access | 0 |  | WiFi included
USD to GBP | 1.27
Lodge rental (GBP, incl VAT) | 19330
Lodge rental (USD, incl VAT) | 24549.1
catering 8h GBP, incl VAT | 39 | breakfast, lunch, 3 breaks
Catering 8h (USD per day) | 49.53
catering dinner (GBP, incl VAT) | 33
catering dinner USD incl VAT) | 41.91
Catering Total | 32156.4
Meeting Rooms (GBP, incl VAT per day) | 8250
Meeting Rooms (USD, 5 days) | 52387.5
Total Venue | 109093
registration fee (3%) | 3600

## editors
summit editor funds
Akshay Sharma | 2500
Bjoern Kimminich | 1750
Devesh Bhatt | 1200
Felipe Zipitria | 2500
Mateo Martinez | 2500
Nikita Garia | 1200
11650
extra sponsored
adam | 4000
Avi Douglen | 1000
Bernhard Mueller | 1000
Sven Schleier | 1000
Adrian Winckles | 1000
Ade Yoseman Putra | 1000
Magno Logan | 1000
10000

## totals
participants
sponsored | 20
tickets paid | 54
invoiced | 21
editors | 6
organizers | 5
funded | 25
total | 131
tickets 24-5 | 15
tickets 24h - Wed | 1
Full week participants | 92

## tickets
tickets sold | price |  | EUR to USD | 1.1
54 | 63255 | 69580.5

## invoiced
participants | tickets | USD | 1.3 | GBP TO USD
capitol one | 6 | 8424
continuum - stephen | 1 | 390
Axa Assistance - Marc | 1 | 1560
PBX | 12 | 9984
1und1 - daniel | 1 | 1560
| 21 | 21918

## sponsored
sponsors | tickets | sponsored
Xebia | 2 | 3500
Toreon | 4 | 7500
Barracuda | 2 | 3500 | Silver
Veracode | 1 | 2750 | Bronze+lanyard+pen
| 9 | 17250
chapters/projects
SAMM | 2 | 10000
London | 0 | 6500
Denver | 0 | 5000
Toreon | 4 | 7500
Xebia | 2 | 3500
Belgium | 1 | 4000 | includes travel for Adam
Germany | 2 | 3900 | includes travel for Ingo and Achim
NY | 0 | 500
Netherlands | 0 | 4000
Luxembourg | 0 | 1500
| 11 | 46400

## funded
# | NAME (TITLE) | PROJECT-LEADER | CHAPTER-LEADER | TIME COVERED BY | TRAVEL FROM | TICKET COST | REQUIRED FUNDS | AMOUNT Summit | amount sponsor | Amount other | WHO FUNDED
1 | Achim Hoffmann | O-Saft |  | vacation | Germany | 1500 | 1950 |  | 1950 |  | OWASP German Chapter
2 | Adam Shostack |  |  |  | Seattle | 1500 | 4000 |  | 4000 |  | OWASP Belgium Chapter
3 | Adrian Winckles |  | Cambridge | ARU | Cambridge | 1500 | 1500 |  |  | 1500 | Owasp Outreach Funds
4 | Akshay Sharma |  | Bhopal | vacation | ???? | 1500 | 2500 | 2500 |  |  | Summit Editor Fund
5 | Avi Douglen |  | Israel | vacation | Israel | 1500 | 2000 |  |  | 2000 | OWASP Community Fund + Israel chapter
6 | Azzeddine Ramrami |  |  |  |  | 1500 | 2400 |  |  | 2400 | CRSFGuard Project
7 | Bernhard Mueller | The OWASP Mobile Security Testing Guide |  | vacation | Singapore | 1500 | 2500 | 1500 |  | 1000 | Summit Budget,OWASP Outreach Funds
8 | Bjoern Kimminich | OWASP Juice Shop |  | vacation | Hamburg | 1500 | 1750 | 1750 |  |  | Summit Editor Fund
9 | Claudia Casanovas |  |  |  |  | 1500 | 1500 |  |  | 1500 | Summit Budget
10 | Daniel Miessler |  |  |  | San Francisco | 1500 | 2500 | 2500 |  |  | Summit Budget
11 | Devesh Bhatt |  |  |  | Bangalore | 0 | 1200 | 1200 |  |  | Summit Editor Fund
12 | Felipe Zipitria |  | Uruguay | vacation | Uruguay | 1500 | 2500 | 2500 |  |  | Summit Editor Fund
13 | Hardik Parekh |  |  |  | United States | 1500 | 2500 | 1000 | 1500 |  | Summit Budget,SAMM
14 | Ingo Hanke |  |  |  | Germany | 1500 | 1950 |  | 1950 |  | OWASP German Chapter
15 | Martin Knoblocj | OWASP Board Member |  |  |  | 1500 |  | 1500 |  | 1500 | Owasp Foundation
16 | Tiffany |  |  |  | United States | 1500 | 1500 |  |  | 1500 | Summit Budget
17 | Marco Morana |  |  | 2 days | Tampa, Florida, USA | 500 | 2441 | 1500 |  | 941 | Summit Budget,CISO Project
18 | Mateo Martinez |  | Uruguay | vacation | Uruguay | 1500 | 2500 | 2500 |  |  | Summit Editor Fund
19 | Nikita Garia |  |  |  | Bangalore | 0 | 1200 | 1200 |  |  | Summit Editor Fund
20 | Sam Stepanyan |  |  |  | London | 400 |  |  |  | 400 | Owasp London Chapter
21 | Sherif Mansour |  |  |  | London | 400 |  |  |  | 400 | Owasp London Chapter
22 | Steven van der Baan | Development Guide, CTF | Cambridge | vacation | Cambridge | 1500 | 1500 | 1500 |  |  | Summit Budget
23 | Sven Schleier | Mobile Security Testing Guide, MASVS, Mobile Hacking Playground |  |  |  | 1500 | 2500 | 1500 |  | 1000 | Summit Budget,OWASP Outreach funds
24 | Timo Pagel |  |  | vacation | Hamburg | 1500 | 1900 | 0 |  | 1900 | Owasp Outreach Funds + Germany (400)
25 | Yan Kravchenko |  |  | vacation | Minneapolis | 1500 | 3000 | 1500 |  | 1500 | Summit Budget,SAMM
[8 empty] | 24150 | 9400 | 17541